## Sheet1
Main Phase | Subtask | Date | Actual Start | Actual End | (Actual)Start Date | (Actual)End Date | (Expected)Start Date | (Expected)End Date | (Expected)Duration | (Actual)Duration
Documentation | Requirement gathering & use case writing | 2001-06-01 | 2025-06-01 | 2025-06-03 | 01-06-2025 | 2025-06-05 | 2025-06-01 | 2025-06-03 | 3 | 5
| Database design, system architecture sketch | 2002-06-01 | 2025-06-04 | 2025-06-04
| Project plan & test case document creation | 2003-06-01 | 2025-06-05 | 2025-06-05
UI/UX Design | Wireframe & page structure in Figma | 2004-06-01 | 2025-06-06 | 2025-06-07 | 2025-06-06 | 2025-06-08 | 2025-06-04 | 2025-06-05 | 2 | 3
| Color theme, fonts, UX flow validation | 2005-06-01 | 2025-06-08 | 2025-06-08
Frontend Development | Setup structure, homepage UI | 2006-06-01 | 2025-06-09 | 2025-06-12 | 2025-06-09 | 2025-06-15 | 2025-06-06 | 2025-06-09 | 4 | 7
| Forms (login, register), validation | 2007-06-01 | 2025-06-13 | 2025-06-13
| Navigation logic and error states | 2008-06-01 | 2025-06-14 | 2025-06-14
| UI testing and debugging | 2009-06-01 | 2025-06-15 | 2025-06-15
Backend Development | API setup (register/login, appointments) | 2010-06-01 | 2025-06-16 | 2025-06-18 | 2025-06-16 | 2025-06-20 | 2025-06-10 | 2025-06-12 | 3 | 4
| DB connection, data validation | 2011-06-01 | 2025-06-19 | 2025-06-19
| API testing with Postman, debug | 2012-06-01 | 2025-06-20 | 2025-06-20
Integration | Connect frontend to backend | 2013-06-01 | 2025-06-21 | 2025-06-22 | 2023-06-21 | 2025-06-23 | 2025-06-13 | 2025-06-14 | 2 | 2
| Test full workflows | 2014-06-01 | 2025-06-23 | 2025-06-23
Testing & Debugging | Functional testing, all user roles | 2015-06-01 | 2025-06-24 | 2025-06-26 | 2025-06-24 | 2025-06-28 | 2025-06-15 | 2025-06-17 | 3 | 3
| Bug fixes, security testing | 2016-06-01 | 2025-06-27 | 2025-06-27
| Responsiveness, browser compatibility | 2017-06-01 | 2025-06-28 | 2025-06-28
Final Review/Deploy | Final check, docs review | 2018-06-01 | 2025-06-29 | 2025-06-30 | 2025-06-29 | 2025-07-01 | 2025-06-18 | 2025-06-19 | 2 | 2
| Deployment on Render or Vercel | 2019-06-01 | 2025-07-01 | 2025-07-01
Buffer/Contingency | Reserved for unexpected bugs or delays | 2020-06-01 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-06-20 | 2025-06-20 | 1 | 1